4 Box Report - 3/1/2017
Team Z – Bob, Sally, Zoe
Overall Status -
A
Mission
1-2 sentences expressing client goals, benefits and key deliverables. Benefits should be measurable whenever possible.
Critical Milestones
Milestone	Due Date	% Complete	Status
Requirements	March 15	35%	A
Architecture	March 15	80%	G
Design	March 21	50%	A
Build	April 15	10%	G
Quality/Test	May 1	10%	G
Final Delivery	May 10	0%	G
Recent Progress
2nd draft of requirements were reviewed 2/19 / Bob completed data model on 2/24 / Client transmitted data to Cornell on 2/25 / Technology stack finalized by team on 2/26 / Sally completed architecture draft on 2/27 / UX and wireframes reviewed by team 3/1
Risks & Issues
Client wants to use immature BI technology. Team evaluating for 1 week. Fallback is Tableau. / Requirements are 2 weeks late. Reducing scope by 3/6 / Design work cannot complete until requirements freeze
Planned Activities (next 2 weeks)
Decision on BI Technology by 3/12 (team, client) / Requirements scope reduced by 3/6 (Bob) / Requirements freeze by 3/22 (Bob, Sally) / Finish data model by 3/21 (Zoe) / Finalize interfaces and Arch document (Sally)
[Speaker Notes: One other tool make you aware of Template for 0ne page project status Busy executives don’t want a long presentation – they want one page $5m project with ROI of X on time – we got all this stuff done. Here are a few risks . Boom.]