## Sheet1
ITEM	Probability	Impact	RISK	Mitigation	Residual Risk
1) Data compromised causing client reputational risk	Moderate	Extreme	HIGH	1) Encrypt data at rest and in transit	LOW
				2) Anaonomize sensitive data
				3) Keep data on secure server

2) Requirements may be late or incomplete	Likely	Major	HIGH	1) Establish hard "freeze date"
				2) Prioritize for scope reduction	MEDIUM

3) Tools are immature or have steep learning curve	Moderate	Major	MEDIUM	1) Establish cutoff date for new tools	LOW
				2) Use tools that are well known by team

4) Workload exceeeds time allowed for project	Likely	Moderate	MEDIUM	1) reduce scope to fit available resources	LOW
				2) Add staff

5) Datacenter or hardware failure causes loss of artifacts	Moderate	Extreme	HIGH	1) Make sure all artifacts are backed up	LOW
				2) use version control (eg. Github)
				3) Make copies of work on separate servers