## Sheet1
Type	No.	Description	Owner	Start date	End date	% Complete	Dependency	Status
Task/Deliverable		REQUIREMENTS		1-Feb	15-Mar	20%
Task	1.1	Goals	ABC	1-Feb	15-Feb	30%
Deliverable	1.2	Specifications	DEF	1-Feb	22-Feb	10%
Deliverable	1.3	Prototype	ABC	1-Feb	15-Mar	10%	1.2
Deliverable	1.4	UX	HIJ	1-Feb	?	0%
Task/Deliverable		ARCHITECTURE		1-Feb	15-Mar	0%
Task	2.1	Tools	ABC	1-Feb	1-Mar	0%
Deliverable	2.2	Environment	ABC	1-Feb	15-Feb	0%	2.1
Task	2.3	SW Stack	HIJ	1-Feb	15-Feb	0%	2.1
Task	2.4	Components	HIJ	1-Feb	15-Feb	0%
Deliverable	2.5	Data Arch	???	1-Feb	1-Mar	0%	1.2
Task/Deliverable		DESIGN		1-Feb	21-Mar	0%
Deliverable	3.1	Data Model	DEF,ABC	15-Jan	15-Mar	0%	2.5
Deliverable	3.2	Wireframes	HIJ	1-Feb	21-Mar	0%	1.4, 1.2
Deliverable	3.3	Interfaces	DEF	1-Feb	15-Mar	0%	2.5
Task/Deliverable		BUILD		15-Mar	15-Apr	0%
Deliverable	4.1	Code	ABC,DEF	15-Mar	?	0%	1.2
Task	4.2	Unit Test	ABC,DEF	1-Mar	?	0%	4.1
Task	4.3	Change Control	ABC,DEF	1-Mar	?	0%
Task/Deliverable		QUALITY ASSURANCE		15-Mar	1-May	0%
Deliverable	5.1	Test plan	HIJ	1-Apr	15-Apr	0%	2.2
Deliverable	5.2	Test cases	HIJ	1-Apr	15-Apr	0%	1.2
Task	5.3	Stress test	HIJ	1-Apr	1-May	0%	4.1
Task	5.4	System Test	HIJ	1-Apr	1-May	0%	4.1,5.2
Task/Deliverable		FINAL DELIVERY		1-May	10-May	0%
Task	6.1	Client Acceptance	ABC	1-May	15-May	0%	5.4
Task	6.2	Rollout	ABC	1-May	15-May	0%	6.1
Deliverable	6.3	Artifacts in Github	ABC	1-May	15-May	0%